{"text_format":"2","workbook":"xlsx","n_sheets":3,"sheets":["Sheet1","Sheet2","Sheet3"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":0,"defined_names":0,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"Sheet1","index":0,"n_rows":37,"n_cols":7,"rows_kept":37,"cut":false,"hidden":false,"merged":[[34,0,36,0],[31,0,33,0],[26,0,30,0],[21,0,25,0],[1,0,2,0],[3,0,7,0],[8,0,11,0],[12,0,16,0],[17,0,20,0]]}
["日期","序号","任务名","本周完成情况","下周计划","状态","优先级"]
["2019年9月第1周",1,"通用写号工具改进：解决纵拓新需求，加入自动读取并存入数据库的功能","已完成并提供给纵拓","需要跟进纵拓使用情况","OPEN"]
[null,2,"梳理和熟悉codec配置方法，优化191和121L音质","措施：\n1.出差纵拓给戴总听191和121L音质，并优化音质；2.跟纵拓工程师学习QACT工具调音质方法。3、已掌握codec配置方法，开始用此方法去优化音质 \n结果：1.戴总说121L音质很好，不用大改，麦克风增益调低一点点即可；191的音质还有提升空间，缺点表现在声音不够混厚，且带有杂音。已定位到该杂音来源，2+1模块无此杂音，1+1有此杂音，需要继续调codec参数优化。2.跟纵拓陈工了解了QACT工具调音质方法。","继续调试优化HS191和HS121音质","OPEN"]
["2019年9月第2周",1,"通用写号工具改进，跟进纵拓使用情况。","纵拓没有提出进一步改进的要求",null,"CLOSE"]
[null,2,"调试优化191和121的LCC 1+1版本音质","音质有略微改善，目前的音质已到可出货状态，正在进一步优化尝试调到更好的音质","继续调试优化HS191和HS121音质，计划下周结项，无论下周末调到哪种程度，都先出版本。","OPEN"]
[null,3,"191入网认证样机准备","已做好样机，并发给天线厂适配天线","跟进天线适配情况","OPEN"]
[null,4,"分析损坏的单片机","已完成，抽测的单片机大部分问题是PSN和IP为空",null,"CLOSE"]
[null,5,"改版191，换功放AW8735试验效果","已完成PCB改版，并嘉立创投板打样5片，下周生产PCB出来直接给中瑞科做样机","跟进样机制作情况，样机出来后调试音质","OPEN"]
["2019年9月第3周",1,"调试维修550主板硬件","发现550主板硬件上存在不少问题，并维修解决，以便软件继续开展调试下去","跟进550软硬件情况","OPEN"]
[null,2,"调试优化191和121的LCC 1+1版本音质","已基本确定CODEC参数","下周出软件版本","OPEN"]
[null,3,"191入网认证样机准备","样机已给到天线厂","跟进天线适配情况","OPEN"]
[null,4,"改版191，换功放AW8735试验效果","PCBA已到中瑞科，中瑞科正在制作样机","跟进样机制作情况，样机出来后调试音质","OPEN"]
["2019年9月第4周",1,"跟进550软硬件情况","基本功能已通，先出软件版本给健步",null,"CLOSE"]
[null,2,"调试优化191和121的LCC 1+1版本音质","出软件版本",null,"CLOSE"]
[null,3,"191入网认证样机准备","已收到安弗特打样的20片天线样品","用收到的天线样品，制作16台认证用样机","OPEN"]
[null,4,"改版191，换功放AW8735试验效果","PCBA已到中瑞科，中瑞科正在制作样机","跟进样机制作情况，样机出来后调试音质","OPEN"]
[null,5,"分析处理HS580前两三秒录制音量小的问题","已找到调整的寄存器，输出新版本修复问题",null,"CLOSE"]
["2019年10月第2周",1,"191入网认证样机准备","已收到安弗特打样的20片天线样品","用收到的天线样品，制作16台认证用样机","OPEN"]
[null,2,"改版191，换功放AW8735试验效果","样机硬件已完成，出软件版本升级测试","跟进样机制作情况，样机出来后调试音质","OPEN"]
[null,3,"HS580防爆板样机制作","已收到从健步寄来的PCBA及配件，拿到海恒通改DMR模块并组装测试","跟进HS580防爆板制作情况","OPEN"]
[null,4,"路由器新版调试","路由器新版硬件调试","路由器软件功能完善","OPEN"]
["2019年10月第3周",1,"191入网认证样机准备","已完成样机制作",null,"CLOSE"]
[null,2,"改版191，换功放AW8735试验效果","已调试完毕，确定使用AW8735功放",null,"CLOSE"]
[null,3,"HS580防爆板样机制作","等待海恒通制作模块样品","等待海恒通制作模块样品","OPEN"]
[null,4,"路由器软件功能完善","路由器软件功能完善","路由器软件功能完善","OPEN"]
[null,5,"优化消除HS580和HS191底噪","HS580和HS191都存在底噪，尝试调CODEC参数优化","HS580和HS191都存在底噪，尝试调CODEC参数优化","OPEN"]
["2019年10月第4周",1,"HS580防爆板样机制作","已收到海恒通寄来的DMR模块，组装测试","组装测试","OPEN"]
[null,2,"优化消除HS580和HS191底噪","已完成191优化","继续进行580优化","OPEN"]
[null,3,"HS191L使用AW8735功放的版本，插耳机时有电流声，待分析解决","分析插耳机的电流声","分析插耳机的电流声","OPEN"]
[null,4,"HS580上验LCC封装龙尚模块,并给样机天线厂测试天线指标","收到LCC模块，已完成样机制作并寄给玛雅测试",null,"CLOSE"]
[null,5,"HS580座充问题分析优化","分析出HS580座充的问题点，提出了优化整改建议，并把整改建议输出给健步",null,"CLOSE"]
["2019年11月第1周",1,"银川客户反馈HS151待机时间短","测试151电池容量,测得容量为3795mAh",null,"CLOSE"]
[null,2,"HS121L+LCC模块调音质","已调好",null,"CLOSE"]
[null,3,"HS580防爆板样机制作","HS580防爆板样机功能调试","HS580防爆板样机功能调试","OPEN"]
["2019年11月第2周",1,"HS580座充优化","测试优化后的座充样机，发现温度还是偏高，分析出是MOS驱动效率不高，改驱动电路后，发热降低。还存在纹波较大的问题。","分析纹波较大的问题","OPEN"]
[null,2,"HS580防爆板样机制作","HS580防爆板样机功能调试","HS580防爆板样机功能调试","OPEN"]
[null,3,"出差跟进HS191+LCC模块首次量产","已顺利出货",null,"CLOSE"]

{"sheet":"Sheet2","index":1,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":false,"merged":[]}

{"sheet":"Sheet3","index":2,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":false,"merged":[]}